## Projected
|  | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30
WP | Task | Mnt1 | Mnt2 | Mnt3 | Mnt4 | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34
Research
Read past relevant studies | bar: 2021-06-01 to 2022-01-17
Gathering Ground Truth Data | bar: 2021-10-04 to 2021-10-25
Mentor meetings
Hold weekly meetings | bar: 2021-10-11 to 2022-05-30
ARPA meeting and contact | bar: 2021-10-18; 2021-11-08
Deliverables
Record prototype | bar: 2022-05-30
Upload VIVA | bar: 2022-05-30
Submit report
Research Methodology
Hypothesis | bar: 2022-02-14 to 2022-02-28
Research Questions | bar: 2022-02-21 to 2022-02-28
Research Methods | bar: 2022-02-28
Research Pipeline
Finalise section in report
Literature Review
Review datasets | bar: 2021-11-08 to 2021-11-29; 2021-12-20
Review algorithms | bar: 2021-11-22 to 2022-01-10
Review evaluation metrics | bar: 2022-01-17 to 2022-01-24
Finalise section in report
Prototype
Find tutorial | bar: 2021-10-18 to 2021-10-25
Replicate tutorial | bar: 2021-10-25 to 2021-11-08
Create custom dataset | bar: 2021-11-15 to 2021-11-29; 2021-12-20 to 2022-01-03
Tweek prototype | bar: 2021-11-15 to 2021-12-13; 2021-12-27 to 2022-01-31
Generate evaluation results
Discussion of Results
Write prototype evaluation | bar: 2022-03-14 to 2022-03-21
Write dataset evaluation | bar: 2022-03-21 to 2022-03-28
Write hypothesis testing | bar: 2022-03-28 to 2022-04-04
Write project evaluation | bar: 2022-04-04 to 2022-04-18
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: 2022-05-09 to 2022-05-16
Finalise Introduction | bar: 2022-05-16 to 2022-05-23
Finalise Abstract

## Actual
|  | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30
WP | Task | Mnt1 | Mnt2 | Mnt3 | Mnt4 | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14 | WK15 | WK16 | WK17 | WK18 | WK19 | WK20 | WK21 | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34
Research
Read past relevant studies | bar: 2021-07-01; 2021-09-01; 2021-10-25; 2021-11-08; 2021-11-22; 2021-12-06 to 2021-12-13; 2022-01-17 to 2022-01-31
Gathering Ground Truth Data | bar: 2021-10-18 to 2021-10-25
Meetings
Hold weekly mentor meetings | bar: 2021-10-11 to 2022-03-07
ARPA meeting and contact | bar: 2021-11-01 to 2021-11-08; 2021-11-29 to 2021-12-06
Deliverables
Record prototype
Upload VIVA
Submit report
Research Methodology
Hypothesis | bar: 2022-03-07
Research Questions | bar: 2022-03-07
Research Methods | bar: 2022-03-07
Research Pipeline | bar: 2022-03-07
Finalise section in report | bar: 2022-03-07
Literature Review
Review datasets | bar: 2022-01-03 to 2022-01-17
Review algorithms | bar: 2022-01-10 to 2022-01-24
Review evaluation metrics | bar: 2022-01-17 to 2022-01-24
Finalise section in report | bar: 2022-01-31 to 2022-02-07
Prototype
Find tutorial | bar: 2021-10-25 to 2021-11-01
Replicate tutorial | bar: 2021-11-08 to 2021-11-15; 2021-12-20 to 2021-12-27; 2022-01-31 to 2022-02-07
Create custom dataset | bar: 2021-11-15 to 2021-11-22; 2021-12-13 to 2021-12-20; 2022-01-31 to 2022-02-07
Tweek prototype | bar: 2021-11-29 to 2021-12-06; 2022-01-24 to 2022-02-21; 2022-03-07
Generate evaluation results | bar: 2022-03-07
Discussion of Results
Write prototype evaluation | bar: 2022-03-07
Write dataset evaluation | bar: 2022-03-07
Write hypothesis testing
Write project evaluation
Finalise section in report
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations
Finalise Introduction
Finalise Abstract